## Introduction
The Continuous Improvement Committee is a committee of the Illinois Workforce Initiative Board. The Illinois Workforce Innovation Board (“IWIB”) is a State of Illinois advisory board pursuant to the Illinois Workforce Innovation Board Act, 20 ILCS 3975/1 et seq. Each Committee of the IWIB is required to develop a Work Plan that tracks the committee’s progress, that outlines alignment with the strategic plan/state unified plan, and that can be used to keep the Board appraised of progress.
CIC Charges | The Charges of the CIC are: Charge 1: Evaluation Design. Review evaluation elements of policies, programs, and processes created or overseen by the IWIB to determine the appropriateness of their relationship to their expected outcomes. Provide feedback and recommendations. Charge 2: Evaluation Outcomes. Review outcomes of evaluation to determine if results conformed to intended outcome. Provide feedback and recommendations. Charge 3: Continuous Improvement at Local Level. Review local performance related to the six federal performance measures for the WIOA core partners and make recommendations about strategies for continuous improvement at local levels. Charge 4: Benchmarks. Examine and evaluate workforce quality and earning benchmarks and recommend changes. Charge 5: Data Recommendations. Provide Recommendations for Readily Accessible Data and technical assistance recommendations for an intended audience. Charge 6: Priority Activities. Manage priority activities as assigned by the IWIB Strategic plan.
Priorities of the CIC: | 1. Policy evaluation 2. Develop an understanding of how WIOA programs (under Title One, Two, Three and Four) are evaluated, what continuous improvement processes are in place and included, and what Technical Assistance from the lead agency is involved. 3. Provide the IWIB Committees with a Clear understanding of how outcomes are evaluated – defining the process for upcoming policy.

## Objective 1
Objective 1: Accelerate and Streamline Communication and Services with Business Partners
Priority Activity 1.1: Develop methodologies to assess employer needs and speed response times
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | Associated CIC Charge
Strategic Direction 1: Support the technology committee and evaluate outcomes | Assign a liaison to the technology committee to ensure alignment of work between the two committees and maintain open communication. |  |  |  |  | Charge 6: Priority Activities
| Review outcomes of technology sub committee's work |  |  |  |  | Charge 2: Evaluation Outcomes
Strategic Direction 1: Develop report formats to analyze and distribute profile and performance information | Recommend reassignment of report creation to another committee or delegation to staff expert. |  |  |  |  | Charge 5: Data Recommendations
| Creation of report format to communicate information to partners |  | Report formats |  |  | Charge 5: Data Recommendations
| Seek clarification on requirements of profile from agency partners |  |  |  |  | Charge 6: Priority Activities
Priority Activity 1.4: Identify key industry sectors and ensure they are the focus of workforce development efforts.
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | Associated CIC Charge
Strategic Direction 1: Identify available data and key sectors | Review work from Title 1 and Title 3 agency partners and response to EO 3. |  |  |  |  | Charge 3: Continuous Improvement at Local Level
| Suggest reassignment of sector identification of industry sectors during strategic plan revision process |  |  |  |  | Charge 5: Data Recommendations
Strategic Direction 2: Use program assessment to ensure focus on industry sectors and ROI. | Implement a program assessment process that aligns with current accountability work taking place at agency partners. |  | TBD after coordination with core partner agencies | 2019-12-31 |  | Charge 2: Evaluation Outcomes

## Objective 3
Objective 3: Sustainable Methods for High Quality Data Collection and Accessible Reporting
Priority Activity 3.1: Forecast the capture, maintenance and utilization of data flows to customers.
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | Associated CIC Charge
Strategic Direction 1: Identify and distinguish helpful performance, labor market information, trend, and interaction data items for different customer groups | Review work from Title 1 and Title 3 agency partners and response to EO 3. |  |  |  |  | Charge 4: Benchmarks.
| Suggest reassignment of sector identification of industry sectors during strategic plan revision process |  |  |  |  | Charge 3: Continuous Improvement at Local Level
Strategic Direction 2: Enhance career exposure, exploration, and development resources for all populations | TBD

## Objective 4
Objective 4: Increase Board Effectiveness Through High Quality Training and Resources for the State Board and Local Workforce Boards
Priority Activity 4.1: Initial and continuing training for board members
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | Associated CIC Charge
Strategic Direction 1: Professional Development oversight | Delegate the responsibility of PD creation to staff and agency projects - provide guidance as necessary |  | Board Member Manual/ Online training for board members |  | 2019-06-19 | Charge 3: Continuous Improvement at Local Level
| Evaluate PD for state and local boards |  |  |  | Ongoing | Charge 2: Evaluation Outcomes
Priority Activity 4.2: Build clarity and understanding between IWIB and LWIB members
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | Associated CIC Charge
Strategic Direction 1: Evaluate methods | EAC will evaluate plans, methods, or processes of communication developed by the board |  | Evaluation | On Request |  | Charge 2: Evaluation Outcomes
Priority Activity 4.3: Ensure that board members have the data they need to execute their board-related responsibilities.
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | Associated CIC Charge
Strategic Direction 1: | Define metrics and timeframes for keeping the board informed of current data |  | Evaluation | On Request |  | Charge 5: Data Recommendations
| Offer information related to what data is available and how it can be used |  |  |  |  | Charge 5: Data Recommendations
| Advise on the effectiveness of data that is chosen by the board |  |  |  |  | Charge 2: Evaluation Outcomes

## Objective 5
Objective 5: Promote Board and Board Member Accountability
Priority Activity 5.1: Foreground the capture, maintenance and utilization of data flows to customers.
Strategic Direction | Action | Activities | Deliverables | Target Completion Date | Completion Date | CIC Charge
Strategic Direction 1: Ensure board members have the information they need to understand objectives, make decisions, and track progress in advance of board meetings | Ensure processes are in place for the board to understand objectives, make decisions, and track progress. - Review and evaluate outcomes/effectiveness of processes by determining if the board members have the information, they need to understand the issues and take action. |  |  |  | Ongoing | Charge 2: Evaluation Outcomes

## Evaluations
Evaluaton | Activities | Outcomes | Deliverables | Target Completion Date | Completion Date