## Workplan
Red font indicates a change from the initial BEC workplan (May 2020)
| IWIB BUSINESS ENGAGEMENT COMMITTEE: Updated WORKPLAN (JUNE, 2020) |  | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-30 | 2021-06-30 | BEYOND 6/30/21
| PRIORITY AREA 1: Establish and Operate the BEC Effectively | GOAL 1.1: Finalize BEC workplan and methods to implement it.
ACTIVITY 1.1.A.: Develop and approve a BEC work plan that expresses the priorities, goals and activities of the committee.
ACTIVITY 1.1.B.: Review, update and approve the BEC work plan as necessary or appropriate
ACTIVITY 1.1.C.: Establish and support the structure necessary for implementation of the workplan.
GOAL 1.2: Develop and Evolve Committee Membership and Member Expectations.
ACTIVITY 1.2.A.: Determine an initial Committee membership profile.
ACTIVITY 1.2.B.: Develop an set of committee membership expectations, and accountability practices.
ACTIVITY 1.2.C.: Develop mechanisms for identifying replacements for committee vacancies.
ACTIVITY 1.2.D.: Create an orientation for committee members and effectively onboard all members, include an overview of each goal and specifically of the elements of Goal 5 and how they relate to the other goals.
| PRIORITY AREA 2: ENGAGE ILLINOIS' BUSINESS COMMUNITY IN INDUSTRY-LED SECTOR PARTNERSHIPS | GOAL 2.1: Identify Illinois Target Industries & Sectors.
ACTIVITY 2.1.A.: Review and (as appropriate) adopt existing statewide and regionally specific target sectors identified through previous statewide and regional workforce and economic development planning.
ACTIVITY 2.1.B.: Explore changes in sectors across the economy, identify new target industries or adjustments needed to existing as appropriate in alignment with economic conditions.
GOAL 2.2: Increase awareness of and support existing sector strategies.
ACTIVITY 2.2.A.: Support the creation of a directory of existing talent pipeline management projects and other employer-driven sector strategies -- particularly as identified under Goal 2.1.
ACTIVITY 2.2.B.: Identify best practices as opportunities for replication and expansion of existing sector strategies.
ACTIVITY 2.2.C.: Assist existing employer-led workforce development projects in target sector businesses in all regions in Illinois.
GOAL 2.3: Identify and support opportunities for additional sector strategies.
ACTIVITY 2.3.A.: Conduct a gap analysis of 2.1 and 2.2 to identify, target industry sectors in regions across IL for new sector-based activities.
ACTIVITY 2.3.B.: Encourage and support the establishment and sustainability of new sector strategies statewide and within all regions.
ACTIVITY 2.3.C.: Assist appropriate state and regional actors (e.g., LWIBs, Business Associations, Regional Economic Development Organizations, etc.) to develop and promote new employer-led workforce development projects to sector businesses in all regions in Illinois.
GOAL 2.4: Effectively communicate with and aid sector strategies identified under Goal 2.2 and 2.3.
ACTIVITY 2.4.A.: Promote existing and new employer-led workforce development projects to sector businesses in all regions in Illinois.
ACTIVITY 2.4.B: Identify tangible solutions to support businesses affected by economic conditions, such as COVID-19, especially small businesses and utilize sector strategies to promote these offerings.
Activity 2.4.C: Create a network of sector-based community of practice for each target industry of both state and regional players, to support each other and for collaboration to better support partnerships and businesses in each sector.
| PRIORITY AREA 3: COMMUNICATION BETWEEN EMPLOYERS AND THE WORKFORCE DEVELOPMENT SYSTEM | GOAL 3.1: Expand employer knowledge of the workforce and education systems.
ACTIVITY 3.1.A.: Develop mechanisms to determine and assemble information sets regarding these systems that are relevant to employer needs.
ACTIVITY 3.1.B.: Develop mechanisms to transmit those information sets to employers.
GOAL 3.2: Engage employers in identifying and communicating training and workforce needs.
ACTIVITY 3.2.A.: Support the utilization of sector strategies and business services to engage employers and help them identify and communicate their needs.
ACTIVITY 3.2.B.: Encourage the development of a simple and consistent approach for helping identify employer needs and matching those needs to available resources.
GOAL 3.3: Support the development of an employer information database.
ACTIVITY 3.3.A.: Explore and support the development a common database of employer information and contacts with/from workforce development partners at all levels of the workforce development system.
ACTIVITY 3.3.B.: Support creation of a mechanism for sharing up to date information about unified business services efforts, at the regional level and across the state.
GOAL 3.4: Support ongoing employer engagement
ACTIVITY 3.4.A.: Identify opportunities to support and promote unified business services efforts at the state level and in each region of the state.
ACTIVITY 3.4.B.: Develop policies to support engagement between employers and the workforce/economic development system and strengthen communication between system partners.
ACTIVITY 3.4.C.: Identify and implement a framework to assist business advocates of the system to promote the workforce and education system services to their industries and peers.
GOAL 3.5: Explore, and if viable, promote an initiative to provide common messaging and shared branding across all system partners.
ACTIVITY 3.5.A.: Identify best practices for shared branding and messaging.
ACTIVITY 3.5.B.: Explore a collaborative solution across all partners for messaging and branding employer services, that will elevate the system partners "above the noise" and provide a "stamp of approval" that helps businesses identify system resources.
| PRIORITY AREA 4: ASSIST IWIB AND LWIB OUTREACH, RECRUITMENT AND COMMUNICATION | GOAL 4.1: Assist IWIB/LWIB recruitment, engagement, retention, and accountability.
ACTIVITY 4.1.A.: Develop outreach mechanisms and other tools to assist in the recruitment of employers to the IWIB and the LWIBs.
ACTIVITY 4.1.B.: Develop a framework for effective engagement and retention of business representatives of workforce boards.
GOAL 4.2: Enhance IWIB/LWIB Communication
ACTIVITY 4.1.A.: Develop and expand mechanisms to ensure consistent and timely communication between LWIBs and the IWIB.
| PRIORITY AREA 5: COORDINATION WITH RELATED GROUPS AND ACTIVITIES | GOAL 5.1: Coordinate with Executive Order #3 Activities
ACTIVITY 5.1.A.: Review Executive Order #3 activities and recommend approaches by which the BEC can assist in their completion.
ACTIVITY 5.1.B.: Acquire an overview and 101 training to be used in the committee onboarding orientation.
GOAL 5.2: Coordinate with WIOA State Unified Plan Activities
ACTIVITY 5.2.A.: Review WIOA State Unified Plan activities and recommend approaches by which the BEC can assist in their completion.
ACTIVITY 5.2.B.: Create an overview and 101 training to be used in the committee onboarding orientation.
GOAL 5.3: Coordinate with Restore Illinois Health Plan Activities
ACTIVITY 5.3.A.: Review Restore Illinois Health Plan activities and recommend approaches by which the BEC can assist in their completion.
ACTIVITY 5.3.B.: Recommend approaches to communicate available COVID-19-related business assistance to employers.
ACTIVITY 5.3.C.: Create an overview and 101 training to be used in the committee onboarding orientation.
GOAL 5.4: Coordinate with Activities of Other IWIB Committees
ACTIVITY 5.4.A.: Coordinate, as appropriate, with the other IWIB Committees, Work Groups and Task Forces in order to ensure successful completion of the activities of all IWIB groups.
ACTIVITY 5.4.B.: Create an overview and 101 training to be used in the committee onboarding orientation.
Activity Completed
Activity in progress during this quarter & on schedule
Activity in progress during this quarter & behind schedule
Activity due to be in progress during this quarter but not yet begun
Activity to be in progress during this quarter
Activity not yet begun during this quarter

## Priority 1
IWIB BUSINESS ENGAGEMENT COMMITTEE: Updated WORKPLAN (June 2020) |  | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-30 | 2021-06-30 | BEYOND 6/30/21
PRIORITY AREA 1: Establish and Operate the BEC Effectively | GOAL 1.1: Finalize BEC workplan and methods to implement it.
ACTIVITY 1.1.A.: Develop and approve a BEC work plan that expresses the priorities, goals and activities of the committee.
TACTIC 1.1.A.i: Conduct member focus groups to gather feedback on the workplan and recommended tactics.
TACTIC 1.1.A.ii: Share feedback with the full committee, discuss potential modifications to the workplan.
TACTIC 1.1.A.iii: Update workplan and prepare to present it to the IWIB Executive Committee.
TACTIC 1.1.A.iv.: Present to the Executive Committee.
TACTIC 1.1.A.v.: Revise and finalize work plan as needed.
ACTIVITY 1.1.B.: Review, update and approve the BEC work plan as necessary or appropriate
TACTIC 1.1.B.i: At each quarterly committee meeting, review the committee workplan including updates and consideration of any adjustments needed.
ACTIVITY 1.1.C.: Establish and support the structure necessary for implementation of the workplan.
TACTIC 1.1.C.i: Establish three workgroups of the committee aligned with the three main priorities (Sectors, Communications, Board Member Engagement).
TACTIC 1.1.C.ii: Use a method for effective enagement and management in implementing the workplan. One example to consider is the Entrepreneurial Operating System for Businesses (EOS).
GOAL 1.2: Develop and Evolve Committee Membership and Member Expectations.
ACTIVITY 1.2.A.: Determine an initial Committee membership profile.
TACTIC 1.2.A.i:
TACTIC 1.2.A.ii: Identify expertise needed beyond committee members and establish mechanisms to engage that expertise as needed. This could include additional industries, public partners, etc.
ACTIVITY 1.2.B.: Develop an set of committee membership expectations and accountability practices.
TACTIC 1.2.B.i:
ACTIVITY 1.2.C.: Develop mechanisms for identifying replacements for committee vacancies.
TACTIC 1.2.C.i:
ACTIVITY 1.2.D.: Create an orientation for committee members and effectively onboard all members, include an overview of each goal and specifically of the elements of Goal 5 and how they relate to the other goals.
TACTIC 1.2.D.i: Create and provide a committee member orientation including a review of the workplan, member expectations, and a 101 training on each of the goals in Priority Area 5 (EO #3, WIOA, Restore Illinois, IWIB Committees).
Activity Completed
Activity in progress during this quarter & on schedule
Activity in progress during this quarter & behind schedule
Activity due to be in progress during this quarter but not yet begun
Activity to be in progress during this quarter
Activity not yet begun during this quarter

## Priority 2
IWIB BUSINESS ENGAGEMENT COMMITTEE: Updated WORKPLAN (June 2020) |  | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-30 | 2021-06-30 | BEYOND 6/30/21
PRIORITY AREA 2: ENGAGE ILLINOIS' BUSINESS COMMUNITY IN INDUSTRY-LED SECTOR PARTNERSHIPS | GOAL 2.1: Identify Illinois Target Industries & Sectors.
ACTIVITY 2.1.A.: Review and (as appropriate) adopt existing statewide and regionally specific target sectors identified through previous statewide and regional workforce and economic development planning.
TACTIC
ACTIVITY 2.1.B.: Explore changes in sectors across the economy, identify new target industries or adjustments needed to existing as appropriate in alignment with economic conditions.
TACTIC
GOAL 2.2: Increase awareness of and support existing sector strategies.
ACTIVITY 2.2.A.: Support the creation of a directory of existing talent pipeline management projects and other employer-driven sector strategies -- particularly as identified under Goal 2.1.
TACTIC 2.2A.i: Research the McLean County mapping project, as a potential model for expansion.
ACTIVITY 2.2.B.: Identify best practices as opportunities for replication and expansion of existing sector strategies.
TACTIC
ACTIVITY 2.2.C.: Assist existing employer-led workforce development projects in target sector businesses in all regions in Illinois.
TACTIC
GOAL 2.3: Identify and support opportunities for additional sector strategies.
ACTIVITY 2.3.A.: Conduct a gap analysis of 2.1 and 2.2 to identify, target industry sectors in regions across IL for new sector-based activities.
TACTIC
ACTIVITY 2.3.B.: Encourage and support the establishment and sustainability of new sector strategies statewide and within all regions.
TACTIC
ACTIVITY 2.3.C.: Assist appropriate state and regional actors (e.g., LWIBs, Business Associations, Regional Economic Development Organizations, etc.) to develop and promote new employer-led workforce development projects to sector businesses in all regions in Illinois.
TACTIC
GOAL 2.4: Effectively communicate with and aid sector strategies identified under Goal 2.2 and 2.3.
ACTIVITY 2.4.A.: Promote existing and new employer-led workforce development projects to sector businesses in all regions in Illinois.
TACTIC
ACTIVITY 2.4.B: Identify tangible solutions to support businesses affected by economic conditions, such as COVID-19, especially small businesses and utilize sector strategies to promote these offerings.
TACTIC
Activity 2.4.C: Create a network of sector-based community of practice for each target industry of both state and regional players, to support each other and for collaboration to better support partnerships and businesses in each sector.
TACTIC
Activity Completed
Activity in progress during this quarter & on schedule
Activity in progress during this quarter & behind schedule
Activity due to be in progress during this quarter but not yet begun
Activity to be in progress during this quarter
Activity not yet begun during this quarter

## Priority 3
IWIB BUSINESS ENGAGEMENT COMMITTEE: Updated WORKPLAN (June 2020) |  | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-30 | 2021-06-30 | BEYOND 6/30/21
PRIORITY AREA 3: COMMUNICATION BETWEEN EMPLOYERS AND THE WORKFORCE DEVELOPMENT SYSTEM | GOAL 3.1: Expand employer knowledge of the workforce and education systems.
ACTIVITY 3.1.A.: Develop mechanisms to determine and assemble information sets regarding these systems that are relevant to employer needs.
TACTIC
ACTIVITY 3.1.B.: Develop mechanisms to transmit those information sets to employers.
TACTIC 3.1.B.i.: Explore the creation of a centralized website where employers can drill down to their specific needs; develop action plan for grassroots networking; implement ambassador program, develop a marketing plan or calendar to disseminate success stories (newsletter, video, social media?)
TACTIC 3.1.B.ii.: Create an directory of business services staff across all partners, make it simple and easy for any partner to direct a business to the right person for help. Embed the directory throughout the above mentioned website, so at any point during navigation the business can easily identify a person to contact for support.
GOAL 3.2: Engage employers in identifying and communicating training and workforce needs.
ACTIVITY 3.2.A.: Support the utilization of sector strategies and business services to engage employers and help them identify and communicate their needs.
TACTIC
ACTIVITY 3.2.B.: Encourage the development of a simple and consistent approach for helping identify employer needs and matching those needs to available resources.
TACTIC
GOAL 3.3: Support the development of an employer information database.
ACTIVITY 3.3.A.: Explore and support the development a common database of employer information and contacts with/from workforce development partners at all levels of the workforce development system.
TACTIC
ACTIVITY 3.3.B.: Support creation of a mechanism for sharing up to date information about unified business services efforts, at the regional level and across the state.
TACTIC
GOAL 3.4: Support ongoing employer engagement
ACTIVITY 3.4.A.: Identify opportunities to support and promote unified business services efforts at the state level and in each region of the state.
TACTIC 3.4.A.i: Use businesses to tell the story of available business services.
TACTIC 3.4.A.ii: Create a simple toolkit for business members to use in their advocacy. Include: - Reminders to "always wear your workforce/education hat" - this might be a lapel pin or some other mechanism that indicates "ask me" - An elevator speech on the system and what it can do for business. - Short but more detailed talking points for use in meetings, at events, etc. - Short video's of businesses telling their story about how the system helped them. - Simple factsheets on resources and contact information for staff.
ACTIVITY 3.4.B.: Develop policies to support engagement between employers and the workforce/economic development system and strengthen communication between system partners.
TACTIC
ACTIVITY 3.4.C.: Identify and implement a framework to assist business advocates of the system to promote the workforce and education system services to their industries and peers.
TACTIC
GOAL 3.5: Explore, and if viable, implement an initiative to provide common messaging and shared branding across all system partners.
ACTIVITY 3.5.A.: Identify best practices for shared branding and messaging.
TACTIC
ACTIVITY 3.5.B.: Explore a collaborative solution across all partners for messaging and branding employer services, that will elevate the system partners "above the noise" and provide a "stamp of approval" that helps businesses identify system resources.
TACTIC
Activity Completed
Activity in progress during this quarter & on schedule
Activity in progress during this quarter & behind schedule
Activity due to be in progress during this quarter but not yet begun
Activity to be in progress during this quarter
Activity not yet begun during this quarter

## Priority 4
IWIB BUSINESS ENGAGEMENT COMMITTEE: Updated WORKPLAN (June 2020) |  | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-30 | 2021-06-30 | BEYOND 6/30/21
PRIORITY AREA 4: ASSIST IWIB AND LWIB OUTREACH, RECRUITMENT AND COMMUNICATION | GOAL 4.1: Assist IWIB/LWIB recruitment, engagement, retention, and accountability.
ACTIVITY 4.1.A.: Develop outreach mechanisms and other tools to assist in the recruitment of employers to the IWIB and the LWIBs.
TACTIC
ACTIVITY 4.1.B.: Develop a framework for effective engagement and retention of business representatives of workforce boards.
TACTIC 4.1.B.i: Define the profile of a local or state board member.
TACTIC 4.1.B.ii: Establish member roles, responsibilities and expectations.
TACTIC 4.1.B.iii: Create policies and procedures for accountability.
TACTIC 4.1.B.iv: Create an effective board member orientation and onboarding as a template for all boards.
GOAL 4.2: Enhance IWIB/LWIB Communication
ACTIVITY 4.1.A.: Develop and expand mechanisms to ensure consistent and timely communication between LWIBs and the IWIB.
TACTIC
Activity Completed
Activity in progress during this quarter & on schedule
Activity in progress during this quarter & behind schedule
Activity due to be in progress during this quarter but not yet begun
Activity to be in progress during this quarter
Activity not yet begun during this quarter

## Priority 5
IWIB BUSINESS ENGAGEMENT COMMITTEE: Updated WORKPLAN (June 2020) |  | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-30 | 2021-06-30 | BEYOND 6/30/21
PRIORITY AREA 5: COORDINATION WITH RELATED GROUPS AND ACTIVITIES | GOAL 5.1: Coordinate with Executive Order #3 Activities
ACTIVITY 5.1.A.: Review Executive Order #3 activities and recommend approaches by which the BEC can assist in their completion.
TACTIC
ACTIVITY 5.1.B.: Acquire an overview and 101 training to be used in the committee onboarding orientation.
TACTIC
GOAL 5.2: Coordinate with WIOA State Unified Plan Activities
ACTIVITY 5.2.A.: Review WIOA State Unified Plan activities and recommend approaches by which the BEC can assist in their completion.
TACTIC
ACTIVITY 5.2.B.: Acquire an overview and 101 training to be used in the committee onboarding orientation.
TACTIC
GOAL 5.3: Coordinate with Restore Illinois Health Plan Activities
ACTIVITY 5.3.A.: Review Restore Illinois Health Plan activities and recommend approaches by which the BEC can assist in their completion.
TACTIC
ACTIVITY 5.3.B.: Recommend approaches to communicate available COVID-19-related business assistance to employers.
TACTIC
ACTIVITY 5.3.C.: Acquire an overview and 101 training to be used in the committee onboarding orientation.
TACTIC
GOAL 5.4: Coordinate with Activities of Other IWIB Committees
ACTIVITY 5.4.A.: Coordinate, as appropriate, with the other IWIB Committees, Work Groups and Task Forces in order to ensure successful completion of the activities of all IWIB groups.
TACTIC
ACTIVITY 5.4.B.: Acquire an overview and 101 training to be used in the committee onboarding orientation.
TACTIC
Activity Completed
Activity in progress during this quarter & on schedule
Activity in progress during this quarter & behind schedule
Activity due to be in progress during this quarter but not yet begun
Activity to be in progress during this quarter
Activity not yet begun during this quarter